## Main sheet
Week | Tasks | Difficulty
2023-05-22 | Create spreadsheet of project plan | Easy
| Create trello board | Easy
| Create new Git repo | Easy
2023-05-29 | Create two branches, one main, one ci-to-git-action (demo code) | Easy
| Run app on local env | Medium
| Run app on Azure | Medium
2023-06-05 | Set up GitHub Actions | Medium
| Test Github Action | Medium
| Create the App Service in Azure | Easy
| Test the app Services | Medium
| Set up the Azure DevOps pipeline | Medium
2023-06-10 | Create Diagram | Easy
| Screenshots | Easy
| Modified Readme file | Easy
| Record a video demo and upload to Youtube | Easy
Goals
Submit project
Q2 plan | Complete project
Yearly plan | Review the code, maintain it
Q1 | learn how to use azure | Easy
Q2 | learn devops and how to plan work | Easy
Q3 | Complete MOCK project | Medium
Q4 | deploy real app | Medium